## Reshaped_Timeline_Data
Task | Month | Status | Due Date
SCRE bathymetry | Oct | P (Oct) | 2024-10-01
Berm topography | Oct | X (Feb) | 2024-10-01
Berm status/breach morphology | Oct | P | 2024-10-01
SCRE water depths | Oct | P | 2024-10-01
Groundwater levels | Oct | P | 2024-10-01
River inflow | Oct | P | 2024-10-01
VWRF discharge | Oct | P | 2024-10-01
Continuous monitoring | Oct | ** | 2024-10-01
Vertical profiles | Oct | ** | 2024-10-01
Harmful algal blooms | Oct | -- | 2024-10-01
Beach seine | Oct | P | 2024-10-01
Deep-water seine/mid-water trawl | Oct | -- | 2024-10-01
eDNA | Oct | -- | 2024-10-01
Point Count surveys | Oct | P | 2024-10-01
Aerial survey/Satellite imagery tasking | Oct | P (Dec) | 2024-10-01
Edge habitat surveys | Oct | P | 2024-10-01
X = fieldwork planned | Oct | -- = sampling event was not needed | 2024-10-01
P = fieldwork completed | Oct | ** = alternative data collection method used | 2024-10-01
Berm status/breach morphology | Nov | P | 2024-11-01
SCRE water depths | Nov | P | 2024-11-01
Groundwater levels | Nov | P | 2024-11-01
River inflow | Nov | P | 2024-11-01
VWRF discharge | Nov | P | 2024-11-01
Continuous monitoring | Nov | ** | 2024-11-01
Vertical profiles | Nov | ** | 2024-11-01
Deep-water seine/mid-water trawl | Nov | -- | 2024-11-01
SCRE bathymetry | Dec | -- | 2024-12-01
Berm status/breach morphology | Dec | P | 2024-12-01
SCRE water depths | Dec | P | 2024-12-01
Groundwater levels | Dec | P | 2024-12-01
River inflow | Dec | P | 2024-12-01
VWRF discharge | Dec | P | 2024-12-01
Continuous monitoring | Dec | P | 2024-12-01
Vertical profiles | Dec | P | 2024-12-01
Deep-water seine/mid-water trawl | Dec | -- | 2024-12-01
eDNA | Dec | P | 2024-12-01
Berm status/breach morphology | Jan | P | 2025-01-01
SCRE water depths | Jan | P | 2025-01-01
Groundwater levels | Jan | P | 2025-01-01
River inflow | Jan | P | 2025-01-01
VWRF discharge | Jan | P | 2025-01-01
Continuous monitoring | Jan | ** | 2025-01-01
Vertical profiles | Jan | ** | 2025-01-01
Deep-water seine/mid-water trawl | Jan | -- | 2025-01-01
eDNA | Jan | ? | 2025-01-01
Aerial survey/Satellite imagery tasking | Jan | P (Dec) | 2025-01-01
Berm status/breach morphology | Feb | P | 2025-02-01
SCRE water depths | Feb | P | 2025-02-01
Groundwater levels | Feb | P | 2025-02-01
River inflow | Feb | P | 2025-02-01
VWRF discharge | Feb | P | 2025-02-01
Continuous monitoring | Feb | ** | 2025-02-01
Vertical profiles | Feb | ** | 2025-02-01
Harmful algal blooms | Feb | -- | 2025-02-01
Beach seine | Feb | P | 2025-02-01
Deep-water seine/mid-water trawl | Feb | -- | 2025-02-01
Edge habitat surveys | Feb | P | 2025-02-01
Berm status/breach morphology | Mar | P | 2025-03-01
SCRE water depths | Mar | P | 2025-03-01
Groundwater levels | Mar | P | 2025-03-01
River inflow | Mar | P | 2025-03-01
VWRF discharge | Mar | P | 2025-03-01
Continuous monitoring | Mar | ** | 2025-03-01
Vertical profiles | Mar | ** | 2025-03-01
Beach seine | Mar | -- | 2025-03-01
Deep-water seine/mid-water trawl | Mar | -- | 2025-03-01
Nesting observation surveys | Mar | X | 2025-03-01
CRAM | Mar | -- | 2025-03-01
Berm topography | Apr | X | 2025-04-01
Berm status/breach morphology | Apr | X | 2025-04-01
SCRE water depths | Apr | X | 2025-04-01
Groundwater levels | Apr | X | 2025-04-01
River inflow | Apr | X | 2025-04-01
VWRF discharge | Apr | X | 2025-04-01
Continuous monitoring | Apr | X | 2025-04-01
Vertical profiles | Apr | X | 2025-04-01
Nutrients (grab samples) | Apr | X | 2025-04-01
Chlorophyll-a (grab sample) | Apr | X | 2025-04-01
Nutrients (grab sample) | Apr | X | 2025-04-01
Macroalgae | Apr | X | 2025-04-01
Harmful algal blooms | Apr | X | 2025-04-01
Deep-water seine/mid-water trawl | Apr | -- | 2025-04-01
eDNA | Apr | X | 2025-04-01
Nesting observation surveys | Apr | X | 2025-04-01
Aerial survey/Satellite imagery tasking | Apr | X | 2025-04-01
Habitat/vegetation type mapping | Apr | X | 2025-04-01
Vegetation transects | Apr | X | 2025-04-01
Berm status/breach morphology | May | X | 2025-05-01
SCRE water depths | May | X | 2025-05-01
Groundwater levels | May | X | 2025-05-01
River inflow | May | X | 2025-05-01
VWRF discharge | May | X | 2025-05-01
Continuous monitoring | May | X | 2025-05-01
Vertical profiles | May | X | 2025-05-01
Harmful algal blooms | May | -- | 2025-05-01
Deep-water seine/mid-water trawl | May | -- | 2025-05-01
Nesting observation surveys | May | X | 2025-05-01
Berm status/breach morphology | Jun | X | 2025-06-01
SCRE water depths | Jun | X | 2025-06-01
Groundwater levels | Jun | X | 2025-06-01
River inflow | Jun | X | 2025-06-01
VWRF discharge | Jun | X | 2025-06-01
Continuous monitoring | Jun | X | 2025-06-01
Vertical profiles | Jun | X | 2025-06-01
Deep-water seine/mid-water trawl | Jun | -- | 2025-06-01
eDNA | Jun | ? | 2025-06-01
Nesting observation surveys | Jun | X | 2025-06-01
Berm status/breach morphology | Jul | X | 2025-07-01
SCRE water depths | Jul | X | 2025-07-01
Groundwater levels | Jul | X | 2025-07-01
River inflow | Jul | X | 2025-07-01
VWRF discharge | Jul | X | 2025-07-01
Continuous monitoring | Jul | X | 2025-07-01
Vertical profiles | Jul | X | 2025-07-01
Nutrients (grab samples) | Jul | X | 2025-07-01
Chlorophyll-a (grab sample) | Jul | X | 2025-07-01
Nutrients (grab sample) | Jul | X | 2025-07-01
Macroalgae | Jul | X | 2025-07-01
Harmful algal blooms | Jul | X | 2025-07-01
Deep-water seine/mid-water trawl | Jul | -- | 2025-07-01
Nesting observation surveys | Jul | X | 2025-07-01
Aerial survey/Satellite imagery tasking | Jul | X | 2025-07-01
Berm status/breach morphology | Aug | X | 2025-08-01
SCRE water depths | Aug | X | 2025-08-01
Groundwater levels | Aug | X | 2025-08-01
River inflow | Aug | X | 2025-08-01
VWRF discharge | Aug | X | 2025-08-01
Continuous monitoring | Aug | X | 2025-08-01
Vertical profiles | Aug | X | 2025-08-01
Harmful algal blooms | Aug | -- | 2025-08-01
Deep-water seine/mid-water trawl | Aug | -- | 2025-08-01
Point Count surveys | Aug | X | 2025-08-01
Berm topography | Sep | X | 2025-09-01
Berm status/breach morphology | Sep | X | 2025-09-01
SCRE water depths | Sep | X | 2025-09-01
Groundwater levels | Sep | X | 2025-09-01
River inflow | Sep | X | 2025-09-01
VWRF discharge | Sep | X | 2025-09-01
Continuous monitoring | Sep | X | 2025-09-01
Vertical profiles | Sep | X | 2025-09-01
Nutrients (grab samples) | Sep | X | 2025-09-01
Chlorophyll-a (grab sample) | Sep | X | 2025-09-01
Nutrients (grab sample) | Sep | X | 2025-09-01
Macroalgae | Sep | X | 2025-09-01
Harmful algal blooms | Sep | X | 2025-09-01
Deep-water seine/mid-water trawl | Sep | -- | 2025-09-01
Point Count surveys | Sep | X | 2025-09-01
Vegetation transects | Sep | X | 2025-09-01
SCRE bathymetry | nan | At start of PCAP, then as needed after large river flow events. (In WY2022 was completed in May). Being repeated Oct 2023 (open), then repeated when closed and filled after Winter 23/24.
Berm topography | nan | Three times a year: (1) April 15th or if open, no later than June 1; (2) in September/October prior to seasonal breach; and (3) after the first seasonal breach or Februrary 1, whichever comes first.
Berm status/breach morphology | nan | Ongoing, import monthly data from ArcGIS to PCAP database and HachWIMS
SCRE water depths | nan | Monthly servicing/download.
Groundwater levels | nan | Monthly servicing/download.
River inflow | nan | Annual gage data to be downoaded from VCWPD, and spot check data to be received too.
VWRF discharge | nan | Download monthly data from HachWIMS and add to PCAP database.
Continuous monitoring | nan | Monthly servicing/downloads. (Weekly spot checks when sondes are pulled out.)
Vertical profiles | nan | Handheld YSI to be used for monthly profiles.
Nutrients (grab samples) | nan | Three times a year: April, July, Sept.
Chlorophyll-a (grab sample) | nan | Three baseline grabs per year (April, July, Sept), plus one-two additional grabs for sonde calibration if needed.
Nutrients (grab sample) | nan | Three times a year: April, July, Sept.
Macroalgae | nan | Three times a year: April, July, Sept.
Harmful algal blooms | nan | Three HAB analyses during Chl-a sampling (if blooming/not separate fieldwork): Oct-Mar, Apr-Jun, Jul-Sep. One separate "On-call" in event as-needed.
Beach seine | nan | October and February annually, third optional survey in summer if opened condition (avoid nesting berm).
Deep-water seine/mid-water trawl | nan | **Dropped out of PCAP for now, CDFW take authorization not acquired.
eDNA | nan | Twice per year: October and between April 1 - May 15 - DELAYED DUE TO BERM STILL OPEN. Then opportunistically if steelhead are relocated to estuary.
Nesting observation surveys | nan | Weekly during breeding season (March-July)
Point Count surveys | nan | Weekly during foraging season (August-October)
Aerial survey/Satellite imagery tasking | nan | One imagery capture per year (May-Sept, but ideally Aug/Sept closed condition). Satellite OK, aerial if need high-res repeated. One on-call satellite imagery tasking (for winter/spring open estuary). Aim for quarterly imagery capture.
Habitat/vegetation type mapping | nan | Once per year (late spring/summer).
Vegetation transects | nan | Twice per year: April-May and in September
Edge habitat surveys | nan | Twice per year: February and October. *Survey must occur outside 3/1 - 9/30 along berm due to State Parks permit nesting season buffer restriction.
CRAM | nan | Once during PCAP: Planned for Summer/Fall 2024.
Berm topography | nan | LiDAR survey of berm abd beach by Fugro on 1/7/2023
Aerial survey/Satellite imagery tasking | nan | Satellite captured post-storm 12/18/22
Habitat/vegetation type mapping | nan | Ground Truthing scheduled 5/16/2023
Vegetation transects | nan | 1st round of Veg Transects Scheduled for 5/19/2023
Edge habitat surveys | nan | Edge survey and mudflat measurements/ground-truthing done 2/15 & 2/16